## Slide 1
Engineering Flexibility
in First-of-a-Kind
Spaceflight Missions
Zachary Barnes | Massachusetts Institute of Technology | EM.424
Using Dynamic Reserves &
Flexible Personnel Allocation

## Slide 2
Scenario: A Dual-Subsystem Spacecraft Development Lifecycle
Cruise-stage Subsystem
TRL 3
TRL 4
Lander-stage Subsystem
The mission is paced entirely by the slower of the
two development paths. Any lag in a single subsystem stalls the entire mission, compounding holding costs and delaying utility.
TRL 8: Actual system completed and "flight
through test and demonstration
Both tracks must
cross this threshold
simultaneously.
AND
Launch
Window
Unlocked.
The system will remain at TRL 8 until the 2-year journey to Mars is complete.

## Slide 3
Why Flexibility? (Problem Framing)
An isolated shock in one variable (e.g., funding) mechanically forces schedule dispersion and cost overruns across the entire architecture.

## Slide 4
Model Architecture
Mars Exploration Rover (MER)
Spacecraft Cruise & Lander Stage Subsystem Illustration [1]

## Slide 5
The Baseline Plan (Deterministic Approach)
Expected Launch:
Fiscal Year 8
Nominal, uninterrupted
path to TRL 8
[2]
Key Metrics

## Slide 6
Variables to Monitor:
Variables to Manage:
Key Insight: Economic variables matter,
but schedule-related technical
uncertainties (delays, budget shortfalls)
uniquely extend the 'project tail,'
heavily impacting NPV.
Sensitivity Analysis
∆
∆

## Slide 7
Cumulative Distribution Function
(A ~$93M overrun from baseline)
Accounting for Uncertainty
[2]

## Slide 8
TRL: 7
Staff Count: 120
Allocation Ratio: 0.60
TRL: 5
Staff Count: 80
Allocation Ratio: 0.4
Track Cruise and Lander tracks
separately. Prevents hiding pacing
issues inside a blended 'average
maturity' metric.
Shifting cross-trained staff & resources to the lagging subsystem.
Temporarily increasing staffing threshold when a subsystem severely lags.
Protects against single-year funding
shocks. Unspent authority from high-budget years fills the reserve, which can be used to sustain engineering flow and prevent the TRL engine from stalling in shortfall years
System Flexibility Descriptions

## Slide 9
Year 2
(Shock + Recovery)
Year 1
(Surplus)
Dynamic Reserves: Real Options Concept Description

## Slide 10
Mean NPV: -$1,022M
The Value of Management Real Options
-800M
P10 | P50 | P90:
Cost of Implementation:
$625,000
[2]

## Slide 11
  2. Unmitigated Uncertainty: (Massive downside tail)
NPV Distribution Comparison
  1. Deterministic Baseline:
(A single point in space)
3. Uncertainty with Real Option Implementation:
(Distribution shifted into more positive regime)
Flexibility reduces variance and fundamentally shifts the expected value of the mission.

## Slide 12
Use it or lose it annual budgets
Fixed team sizes and static ratios
Blended average TRL
Accepting schedule slip and holding costs
Pre-defined surge triggers
Dual-track, independent TRLs
Cross-training & flexible reallocation
Dynamic, protected carryover reserves
Comparing Management Approaches:
Rigid & Deterministic vs. Dynamic & Flexible
Funding Strategy
Resource Allocation
Progress Tracking
Response to Delay

## Slide 13
Lessons Learned & Recommendations
Reallocation only works if personnel can move across subsystem boundaries without massive ramp-up losses.
Standardize Shared Assets
Standardize Mechanical and Electrical Ground Support Equipment (MGSE/EGSE) to allow rapid resource shifting between workstreams.
Define reallocation and surge triggers before the project starts to prevent underreaction and executive thrash.
Unspent funds in strong years should be mindfully retained to act as a stabilizing shock absorber for future shortfalls.
The goal is not to eliminate uncertainty, but to design a system capable of responding intelligently if and/or when it is revealed [3].
Cross-Train Technical Staff
Institutionalize Surge Rules
Protect the Reserve

## Slide 14
References:
[3] Richard de Neufville and Stefan Scholtes. Flexibility in Engineering Design. MIT Press, Cambridge, MA, 2011.
[1] NASA Jet Propulsion Laboratory. Illustration of spacecraft sections, n.d. Image credit: NASA/JPL.
[2] MIT System Design and Management. Garage template 2026 version, 2026. Spreadsheet model template used as the basis for the uncertainty and flexibility analysis.
[4] Barnes, Zachary. (2026, March 18). Dynamic Reserves, Surge Staffing, and Flexible Personnel Allocation in Complex Spaceflight Missions [Course report]. Massachusetts Institute of Technology, EM.424.

## Slide 15
Questions?

## Slide 16
Backup Slides

## Slide 17
Expected Launch: Delayed
(e.g., FY 10 or later)
This simulation illustrates the impact of unmitigated risks. Without flexibility, delays in one or both subsystems prevent the mission from reaching the TRL 8 threshold by Fiscal Year 8, resulting in significant schedule slip and cost increase.
Probability of FY 8 Launch: 0%
Key Metrics
[2]

## Slide 18
TRL Lander-stage
Flexibility Enables
TRL 8 Convergence
TRL Cruise-stage
This simulation illustrates the value of flexibility. Pre-defined options allow subsystems to overcome delays, increasing the likelihood that both reach TRL 8 by FY 8, securing the on-time launch window and generating significant mission value.
Probability of FY 8 Launch: 58%
Flexibility NPV:
-$1,022 Million
(+$124 Million above unmitigated uncertainty estimate)
Key Metrics
Expected Launch: FY 8
(On-Time)
[2]

## Slide 19
Real Options to Mitigate Uncertainty